## Marketplace Tasks
Task ID | Phase | Type | Task Title | Description | Reference (if any) | Assigned To | Status | Notes
TSK-001 | Phase 0 - Foundations | Backend | Design seller identity model | Decide whether sellers can be individual creators (not just verified brands) before writing the catalog service — this changes several foreign keys. | m
TSK-002 | Phase 0 - Foundations | Backend | Migration: merch_products & merch_variants tables | Create merch_products and merch_variants tables (SKU, size/color variants, pricing in INR/USD cents, stock_qty, weight, print_file_url, artwork_id link). | Section 04 - Schema additions
TSK-003 | Phase 0 - Foundations | Backend | Migration: print_providers table | Create print_providers table to store POD partner config (Printful/Printify/manual) with integration_type and api_config jsonb. | Section 04 - Schema additions
TSK-004 | Phase 0 - Foundations | Backend | Seller onboarding API + KYC service | Build onboarding API endpoints for new sellers, reusing brand_verification_requests pattern for KYC/KYB where applicable. | Section 01 - Existing INFRA / Section 07 Q1
TSK-005 | Phase 0 - Foundations | Frontend | Seller onboarding UI flow | Build the multi-step seller onboarding screens (profile, payout details, KYC document upload, verification status) consuming the onboarding API. | Section 01 - Existing INFRA / Section 07 Q1
TSK-006 | Phase 0 - Foundations | Frontend | Seller dashboard shell | Scaffold the seller dashboard shell/navigation (products, orders, payouts placeholders) that later phases will fill in. | Section 06 - Phase 0 deliverables
TSK-007 | Phase 1 - Standalone Merch | Backend | Build carts & cart_items tables + API | Create carts and cart_items tables and CRUD endpoints to support persistent multi-item, multi-seller shopping carts (item_type: license or merch_variant). | Section 04 - Checkout schema
TSK-008 | Phase 1 - Standalone Merch | Backend | Split order_items by seller_id | Add seller_id, item_type, merch_variant_id, and cart_id columns to orders/order_items so a single order can span multiple sellers. | Section 04 - Checkout schema
TSK-009 | Phase 1 - Standalone Merch | Backend | Build addresses table + API | Create addresses table and endpoints for buyer shipping addresses (line1/2, city, state, postal_code, country, is_default). | Section 04 - Fulfillment schema
TSK-010 | Phase 1 - Standalone Merch | Backend | Build fulfillments table + manual status update API | Create fulfillments and fulfillment_items tables with manual status update endpoints (fulfillment_type = in_house_stock, no POD integration yet). | Section 06 - Phase 1 deliverables
TSK-011 | Phase 1 - Standalone Merch | Backend | Merch catalog listing API | Build read APIs for browsing/searching the small standalone merch catalog (product + variant listing, filters). | Section 06 - Phase 1
TSK-012 | Phase 1 - Standalone Merch | Frontend | Merch catalog browse & product detail pages | Build the storefront pages for browsing merch products, filtering, and viewing a product detail page with variant (size/color) selection. | Section 06 - Phase 1
TSK-013 | Phase 1 - Standalone Merch | Frontend | Cart UI | Build the cart drawer/page: add/remove items, quantity updates, mixed license + merch_variant line items, multi-seller grouping. | Section 04 - Checkout schema
TSK-014 | Phase 1 - Standalone Merch | Frontend | Checkout flow UI (address + payment) | Build the checkout flow: address selection/entry, order summary split by seller, and payment step. | Section 04 - Fulfillment schema
TSK-015 | Phase 1 - Standalone Merch | Frontend | Buyer address book UI | Build the address book management screen (add/edit/delete/set default) on top of the addresses API. | Section 04 - Fulfillment schema
TSK-016 | Phase 1 - Standalone Merch | Frontend | Seller manual fulfillment/shipping ops UI | Build the internal seller-facing screen to view orders and manually mark fulfillment status (pending/shipped/delivered) with tracking info. | Section 06 - Phase 1 deliverables
TSK-017 | Phase 2 - Fanart-linked Merch + POD | Backend | Integrate Printful/Printify | Build the print-on-demand integration with Printful/Printify, including order-status webhooks (the main async path in the system). | Section 05 - Fulfillment svc / Section 06 - Phase 2
TSK-018 | Phase 2 - Fanart-linked Merch + POD | Backend | Build print_file_url pipeline off cdn_files | Build the pipeline that generates/serves print-ready files from the existing cdn_files asset registry. | Section 06 - Phase 2 deliverables
TSK-019 | Phase 2 - Fanart-linked Merch + POD | Backend | Turn on artwork_id linking on merch_products | Enable linking a merch_product to its originating artwork so contest-winning/brand fanart can be sold as merch. | Section 04 / Section 06 - Phase 2
TSK-020 | Phase 2 - Fanart-linked Merch + POD | Backend | 'Turn artwork into merch' API | Build the backend endpoint(s) that take an approved artwork and generate a draft merch_product/variant with print_file_url set. | Section 06 - Phase 2 deliverables
TSK-021 | Phase 2 - Fanart-linked Merch + POD | Frontend | 'Turn this artwork into merch' creator flow UI | Build the creator-facing flow: pick a product template, preview artwork-on-product mockup, set pricing, and publish the merch listing. | Section 06 - Phase 2 deliverables
TSK-022 | Phase 2 - Fanart-linked Merch + POD | Frontend | POD order status & tracking UI | Surface print-provider order status (in production/shipped/delivered/failed) to buyers and sellers, driven by the webhook-updated fulfillment records. | Section 05 - Fulfillment svc
TSK-023 | Phase 2 - Fanart-linked Merch + POD | Backend | Resolve licensing-before-print question | Determine whether printing someone else's artwork onto merch requires a commercial license purchase or a separate merch-rights grant, and whether merch_products needs a license_id FK. | Open Question #2
TSK-024 | Phase 3 - Payouts, Reviews, Trust | Backend | Build payouts ledger + Stripe Connect transfers | Create the payouts table (gross/platform_fee/net cents, status, stripe_transfer_id) and automate seller payouts against Stripe Connect. | Section 04 - Money schema / Section 06 - Phase 3
TSK-025 | Phase 3 - Payouts, Reviews, Trust | Backend | Define platform fee rule table | Decide whether platform fee is flat or varies by fulfillment/product type (POD margins are thinner than digital licenses) and build the rule table accordingly. | Open Question #3
TSK-026 | Phase 3 - Payouts, Reviews, Trust | Backend | Build product_reviews table + API | Create product_reviews table (reviewer, target_type: artwork/merch_product, order_item_id for verified purchase, rating, body) and endpoints to submit/fetch reviews. | Section 04 - Money schema / Section 06 - Phase 3
TSK-027 | Phase 3 - Payouts, Reviews, Trust | Backend | Extend moderation_queue to merch listings | Extend the existing generic moderation_queue (entity_type/entity_id) to cover merch listing moderation. | Section 06 - Phase 3 deliverables
TSK-028 | Phase 3 - Payouts, Reviews, Trust | Frontend | Seller payouts dashboard | Build the seller-facing payouts screen: pending/paid balances, per-order breakdown, and Stripe Connect payout status. | Section 04 - Money schema / Section 06 - Phase 3
TSK-029 | Phase 3 - Payouts, Reviews, Trust | Frontend | Reviews & ratings UI | Build the review submission form (for verified buyers) and the display of ratings/reviews on artwork and merch product pages. | Section 04 - Money schema / Section 06 - Phase 3
TSK-030 | Phase 3 - Payouts, Reviews, Trust | Frontend | Merch moderation queue UI | Extend the existing moderation admin UI to show and action merch listings alongside other moderation entity types. | Section 06 - Phase 3 deliverables
TSK-031 | Cross-cutting / Open Questions | Backend | Scope international shipping & tax | Decide whether international shipping, customs/duty, and tax-jurisdiction handling are in scope for Phase 1 or explicitly deferred to a later phase. | Open Question #4
TSK-032 | Cross-cutting / Open Questions | Backend | Decide sync vs async architecture boundary | Confirm that only print-provider webhooks and payout triggers are async (via a Postgres outbox table for now); everything else stays synchronous through the gateway. | Section 05 - Service boundaries
TSK-033 | Cross-cutting / Open Questions | Backend | Define service ownership boundaries | Formalize the 5 service boundaries (Catalog, Commerce, Fulfillment, Payouts, Contests+Brand) within the shared Postgres so teams can own a slice without stepping on each other. | Section 05 - Service boundaries diagram
TSK-034 | Cross-cutting / Open Questions | Frontend | API contract review with frontend team | Frontend sync with backend on request/response shapes for cart, checkout, fulfillment, and payouts endpoints before UI build-out per phase. | Section 05 - Service boundaries diagram

## Log Tracker
Dev Log & Tracker
Sprint Week | Task ID/Name | Feature / Project Area | Task Description | Priority | Assigned To | Status | Reviewer | Start Date | Target Completion Date | Completion Date | Pull Request / Merge Link | Progress Notes | Blockers / Issues | Next Steps | Carry Over to Next Week (Y/N)
2026-06-01 | Dev Log & Tracker | Project Management | Create a spreadsheet for tracking development progress weekly and logging changes to the platform code. | Medium | Joey | Complete |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | N/A | Completed after our meeting, sent to the team | N/A | Whole team gets on board and starts using this weekly. | Y
June 5 push | Double footer | Navigation/Menu | Fix the double footers that pop up on multiple pages. | High | Rafay | Complete |  | 2026-06-01 | 2026-06-05 | 2026-06-08
June 5 push | Update Buttons | Home Page | Buttons: for brands, artists, view active | High | Rafay | Complete |  | 2026-06-01 | 2026-06-05 | 2026-06-08
June 5 push | Artist Logos | About | Remove empty artist logos | Medium | Rafay | Complete |  | 2026-06-01 | 2026-06-05 | 2026-06-08
| Brand Properties listed | Super Admin | Have Brand properties listed under brand owners | Low | Dhruv | Complete
| artist button 404 | Super Admin | artist button 404 fix | Low | Dhruv | Complete
| Owner Profile | Brand, Super Admin | Owner profile separate from Brands tab | Low | Dhruv | Complete
| Header/Footer | Brand, Navigation/Menu | No header and footer | Low | Rafay | Complete
2026-06-01 | Website Content Doc | Website Content | Create a doc with content for Dhruv to update including: past campaigns, fan artist users, licensed fan work, etc. | High | Joey | In Progress |  | 2026-06-01 | 2026-06-02 |  | N/A
June 5 push | Nav Bar update | Navigation/Menu | Fix Nav bar to be correct pages in web | High | Rafay | Complete |  | 2026-06-01 |  | 2026-06-08 |  | Desktop verson is complete but mobile version is still old nav bar options.
June 5 push | Button Hover | About | Remove button hover | Medium | Rafay | Complete
June 12 push | Update Image | Guidelines | Update images with ones provided in Whatsapp group | High | Pratyank | Complete |  | 2026-06-08 |  | 2026-06-29
June 12 push | Remove some sections | Guidelines | Remove following sections: Popular IP-Specific Guidelines, Additional Resources | High | Rafay | Complete |  | 2026-06-08 |  | 2026-06-29
June 12 push | Discord link | Guidelines | keep artist community link and add Discord link | Medium | Rafay | Complete |  | 2026-06-08 |  | 2026-06-29
June 12 push | Guidelines PDF | Guidelines | keep addtional resources link to pdf | Medium | Rafay | Complete |  | 2026-06-08 |  | 2026-06-29
June 12 push | Update Section | Guidelines | Update the Ready to submit your fan art? section at the bottom of the page. | High | Pratyank | Complete |  | 2026-06-08 |  | 2026-06-29
June 12 push | Page spacing | Book a Demo | Fix Spacing between top of page and nav bar | Medium | Rafay | Complete |  | 2026-06-08 |  | 2026-06-22 |  | This is fixed on desktop but still showing issues on mobile.
June 12/22 push | Clean up Mobile | Various Pages | Clean up the spacing of headers on each page for Mobile view | High | Pratyank | Complete |  | 2026-06-16 |  | 2026-06-22
June 12/22 push | Mobile page spacing | Book a Demo | Fix spacing on mobile | Medium | Pratyank | Complete |  | 2026-06-08 |  | 2026-06-22 |  | This is fixed on desktop but still showing issues on mobile.
June 12 push | Combine sections | Book a Demo | Combine the Request Your Brand and Book a Demo section into one. Remove the appt options and scheduling and just add that our Team will be in touch to book a demo and then the demo details from the Book a Demo section | High | Rafay | Complete |  | 2026-06-08 |  | 2026-06-29
June 12 push | Add how did you hear about us | Book a Demo | Add Discord and input field for Other options for how did you hear about us | Low | Rafay -> Pratyank | Complete |  | 2026-06-08 |  | 2026-07-30
| Date picker not selecting date | Create Opportunity | Fix error where date picker not selecting date | Medium | Rafay | Not Started
| Days Alignment | Create Opportunity | Fix days alignment off | Medium | Rafay | Not Started
2026-06-08 | Fix upload image | Create Opportunity | upload image not working | Medium | Pratyank | Not Started |  | 2026-06-08
| Create New Accounts (Brand Owners) | Signup/Login, Super Admin | Fix so we can create new accounts with no issues and login to existing accounts with new issues. | Medium | Dhruv -> Jyotishmoy | Complete |  | 2026-06-15 |  | 2026-07-13
| Create New Accounts (Fan Artists) | Signup/Login, Super Admin | Fix so we can create new accounts for fan artists with no issues. | High | Dhruv -> Jyotishmoy | Complete |  | 2026-06-15 |  | 2026-07-13
| Test accounts | Signup/Login, Dashboard | Create test accounts for team to login | High | Dhruv -> Jyotishmoy | Complete |  | 2026-06-15
| Featured Campaigns style | Home Page | Update featured campaigns to remove the infringement images and template campaigns. Replace with feed of current/live campaigns or preset ones from old/new campaigns. | High | Rafay | Complete |  | 2026-06-15 |  | 2026-06-29
| Select Featured Campaigns | Super Admin | Create a function for marking featured campaigns in the Super Admin | High | Dhruv | In Progress |  | 2026-06-15
| Featured Campaigns Section | Home Page | Create section for featured campaigns to display | High | Rafay | Complete |  | 2026-06-15 |  | 2026-06-29
| Backend Migration | Backend | Migrating Node.js to Nest.js server architecture | Medium | Dhruv, Aakash | Blocked |  | 2026-06-15
| Signup Workflow | Signup/Login | Fix the registering of brand owners and fan artists accounts when signing up | Medium | Dhruv, Jyotishmoy | Complete |  | 2026-06-15 |  | 2026-07-13
| Shift Manual Auth to Firebase | Auth | Shift the current manual auth apis to firebase sdk instead | High | Aakash | Complete |  | 2026-06-17 |  | 2026-06-25
| Add Coolify to VPS | Core/Devops | Shift the projects and db to Coolify instead | High | Aakash | Complete |  | 2026-06-17 |  | 2026-06-29
| Make a weekly database backup cron job | DB Backups | Add a weekly automated cron job that makes backup of the db and saves it locally on the VPS itself | Medium | Aakash | Ready for Review |  | 2026-06-17
| Update platform T&S date | Terms of Service | Platform Terms of Service date needs to be fixed: Updated June 23, 2026: https://www.modfanofficial.com/legal/terms-and-service | Medium | Pratyank | Complete |  | 2026-06-25 |  | 2026-06-29
| Transfer/create submission terms of service and link to each Opportunity/contest page | Terms of Service, Opportunity Pages | Make sure the submissions terms of service has it’s own page and is linked for each contest/opportunity page: https://modfanart.com/pages/submission-terms-and-conditions (need to update “MOD INC.” name to “MOD Fan Official”. create a page for contest submissions terms, you can find the terms data in lib/terms-data/contestSubmissionSections.ts and use the terms-section.tsx component to display it | High | Pratyank | Complete |  | 2026-06-25 |  | 2026-06-29
| Authentication for librarians page | Authentication, The Librarians, Opportunty Page | Authentication for the Librarians campaign page. Check if the are logged in for the page. | High | Pratyank | Complete |  | 2026-06-29 |  | 2026-07-13
| Remove Welcome Art | Gallery Page | Remove Welcome Artwork in the gallery | Medium | Pratyank | Complete |  | 2026-06-29 |  | 2026-08-10
| Update Artwork | Gallery Page | Update the artwork and gallery with past winner art. | Low | Joseph, Pratyank | Blocked
| Remove sections in Profile | Profile Settings | Remove API, Billing (can keep hidden for later), and Security (Two Factor Authentication) pages) | Medium | Rafay | Complete | Jyotishmoy | 2026-06-29 |  | 2026-07-20
| Upoad Profile picture | Profile Settings | Fix upload profile picture | High | Rafay, Pratyank | Complete
| Two factor auth | Profile, Security | Setup TFA for users | Low | Aakash | Not Started
| User name visibility fix | All | Fix the visibility of the username on top right for all pages in the Hero section | Low | Pratyank | Complete |  | 2026-06-29 |  | 2026-07-20
| Fix signup | Sign up/ Login | Fix GoogleAuth for signup and login | High | Jyotishmoy | Complete |  | 2026-07-03 |  | 2026-07-13
| Fix Lib contest entry | The Librarians, Submissions | Fix Librarians contest entry button to lead to sign up not submission page | High | Pratyank | Complete |  | 2026-07-03 |  | 2026-07-13
| Get Submission flow ready | Submissions, Dashboard | Ensure submission upload page and workflow is functional and ready | High | Jyotishmoy, Aakash | Complete |  | 2026-07-03 |  | 2026-07-13
| Link T&S to Lib contest | Terms of Service, The Librarians | Link new Submissions terms and conditions page to Librarians contest | High | Pratyank | Complete |  | 2026-07-06 |  | 2026-08-02
| Replace hero image at Signup | Signup/Login | Replace image right side image with logo with new asset provided HERE. | Medium | Pratyank | Complete |  | 2026-07-06 |  | 2026-07-30
| Remove for Creators page on mobile | Menu Bar, Mobile | Remove For Creators page in mobile view | Low | Pratyank | Complete |  | 2026-07-06 |  | 2026-07-20
| Remove hardcoded parts of the Dashboard | Dashboard clean up | Clean up and remove the sections and numbers that are hardcoded in the dashboards | High | Rafay | Complete | Jyotishmoy | 2026-07-08 |  | 2026-07-20
| Create Electric Entertainment brand account | Create EE brand Account | Create EE brand account and librrians brand account | High | Joey | Not Started
| Fix submission images in dashboard | Dashboard, Submissions | Fixing the images that show up on dashboard for submissions | High | Praytank | Complete |  | 2026-07-11 |  | 2026-08-10
| Fix refresh glitch | 404 Page, Login/Signup | When refreshing the website or from a 404 page it automatically brings us to the login/signup page | High | Rafay | Complete |  | 2026-07-11 |  | 2026-07-16
| Allow for multi entry submissions | Contests, Submissions | Allow for multiple entries into the contest for submittors | High | Aakash | Complete |  | 2026-07-13
| Allow for multi submissions | Contests, Submissions | allow for multiple submissions uploaded at a time | High | Aakash | Complete |  | 2026-07-13
| allow for pdf files | Contests, Submissions | allow for pdf files to be uploaded | High | Aakash | Complete |  | 2026-07-13
| increase file sizes for submissions | Contests, Submissions | increase file size of submissions allowed to be uploaded | High | Aakash | Complete |  | 2026-07-13
| Create superadmin login for team | Super Admin | Create new login credentials for workspace.modfanofficial admin/team dashboard | High | Dhruv | In Progress
| Add header and logo nav | Login/Signup | Add the header and logo buttom to head back to main page from the dashboard, login/signup page, to easily navigate back to main page. | Low | Rafay | In Progress |  | 2026-07-13
| Individual submission pages | Dashboard, Submissions, Contests | Build out the individual submission/artwork page with all notes and details | Medium | Rafay | Complete |  | 2026-07-13 |  | 2026-08-10
| Fix submission tags | Contests, Submissions | Submission page tags section is not working | Medium | Pratyank | Complete |  | 2026-07-13 |  | 2026-07-30
| Add description and note to contest entry | Contests, Submissions | Add a Note section to the submission page | Medium | Praytank | Complete |  | 2026-07-13 |  | 2026-07-20
| Setup full contest and submission flow backend | Contests, Submissions, Dashboard | Create proper backend flow for creating new contests and submissions flow correctly connected to it. Review gaps Jyotishmoy shared and what is needed left. | High | Aakash, Jyotishmoy, Pratyank | Ready for Review |  | 2026-07-11
| Link artists and brand owners with contest ID | Contests, Submissions | How to link to artists and brand owners (through the submission?), contest ID to link them all? | Medium | Aakash, Jyotishmoy, Pratyank | Ready for Review |  | 2026-07-11
| Create viewable approved artwork page | Submisions, Dashboard | Where do artwork go and are viewable once approved on brand side. | Medium | Aakash, Jyotishmoy, Pratyank, Rafay |  |  | 2026-07-11
| Link EE account to Librarians contest | Contests | Link new EE account connect the Librarians contest to them to see and setup for approvals/judging. | Medium | Aakash | Blocked |  | 2026-07-13
| Switch domain to hostinger | Server, Domain | Connect domain to hostinger to move away from vercel | High | Aakash | Complete |  | 2026-06-29 |  | 2026-06-30
| Fix submission showing in Gallery | Gallery, Backend | Fixing so submissions don't automatically show up in the main gallery for everyone, they should only show approved and licesned artwork there | High | Pratyank | Ready for Review |  | 2026-07-16
| Fix contest submit art button to dashboard for logged in | Contest Page, Dashboard, Login | if logged in the submit art on contest page takes you to the login page, would be best to take it to dashboard directly to the submit page | Medium | Rafay | Complete
| Login Issues with firebase | Login, User | User getting logged out and also having login in issues using google auth. Seems to be a firebase issue. | Medium | Aakash | Complete |  | 2026-07-16
| Fix Dashboard Setting button | Dashboard | Dashboard setting button on the bottom is fixed and connected to settings page. | Low | rafay |  |  | 2026-07-16
| Update dashboard top right menu to full one | Dashboard | The dropdown menu at top right when clicking name is not appear in the dashboard, have it reappear there | Low | Rafay |  |  | 2026-07-16
| Upload Favicon | Favicon | favicon is missing | Low
| Fix timezone options | Settings, Account | Update Settings so you can choose EST and other timezones. | Low | Rafay
| Fix failed to create artwork issue | Submissions, The Librarians | Failed to create artwork issue coming up for user on mobile and desktop | High | Aakash | Complete
| Complete migration away from AWS | Server | Full complete migration from AWS to Hostinger or other s3 services | High |  | Complete |  | 2026-07-20 |  | 2026-07-30
| Dashboard welcome back name | Dashboard | Dashboard welcome back name hardcoded | Low | Rafay | Complete |  | 2026-07-20
| Old contest page link | Contests | linking to old contest page | Medium | Rafay | Blocked
| Dashboard - View All Submissions | Brand Manager Dashboard | The brand account dashboard currently caps at ~20 submissions with no way to see the rest | High | Pratyank | Complete |  | 2026-07-30 |  | 2026-08-10
| Submission Detail View - Full Image + Form Metadata | Brand Manager Dashboard | Clicking a submission on the dashboard should open a full detail view showing the full-size artwork image plus all metadata | High | Pratyank | Complete |  | 2026-07-30 |  | 2026-08-10
| Fix dashboard images | Dashboard | ⁠ ⁠Fix images showing now loading/showing on the platform dashboards (need to be able to see the entries). | High | Rafay | Complete |  | 2026-07-11 |  | 2026-08-10
| Super admin credentials | Super Admin | Access to the mod super admin workspace. Need the new credentials for this so we can see all users, brand requests, and inquires that have come in through the website. | High | Dhruv |  |  | 2026-07-11
| Submission page details | Submissions | Each submission page that shows that submission image or multiple images, all the inputs from the submission form, and the AI check results. | High | Rafay/Pratyank | Blocked |  | 2026-07-30
| Prepare judging system | Judging | ⁠Prepare the judging system for when librarians contest ends. We will need to send the judging links to the librarians team. | High | Rafay | Complete |  | 2026-07-30 |  | 2026-08-24
| Judging backend endpoints | Backend/Judging | Fix backend enpoints for juding system | High | Pratyank | Complete |  | 2026-08-10 |  | 2026-08-24
| PDF image preview | Submissions | pdf image preview for submissions needs to be fixed, replace with placeholder PDF image so it's not showing like an eerror | Medium | Rafay | Complete |  | 2026-08-10 |  | 2026-08-31
| Judging next phase | Judging | Complete next phase of judging to show results, select final winners, and generate shareable link to view the top 10 (internal link for brand team/final look over). |  | Pratyank | Complete |  | 2026-08-17 |  | 2026-08-24
| AI system UI | Frontend/AI | Create frontend/UI of the AI system and integrating the script into our system. |  | Aakash, Pratyank, Rafay |  |  | 2026-08-24
| Marketplace plan | Marketplace | Next phase Marketplace plan creation and implementation |  | Dhruv |  |  | 2026-08-17
| Copy judging password | Judging | Unable to copy Judging password from popup that appears when creating juding account. |  | Pratyank | Complete |  | 2026-08-17 |  | 2026-08-24
| Brand account creation error | Super Admin/Judging | Error appeared when creating brand account through juding link: Submission failed: Collumn "contact_email"of relation "brand_verification_requests" does not exist |  | Pratyank | Complete
| Login page standard | Login/Backend | Fix login page and backend to industry standard | Low | Dhruv |  |  | 2026-08-24
| Update contest results | Contests | Update contest results with finalized licensing and selected artwork |  | Pratyank | Merged |  | 2026-08-27
| AI system integration | AI | Connect with Aakash on AI system and figure out integration into the front end, for submission checks for campaigns and always on submissions |  | Rafay |  |  | 2026-08-24
| Marketplace tasks | Marketplace | Decide and assign tasks for Marketplace roll out |  | Dhruv |  |  | 2026-08-24
| Licensing workflow doc | Licensing | Assess licensing workflow and create doc to get team aligned |  | Dhruv | Complete |  | 2026-08-24 |  | 2026-08-27
| Github security filtration | Github/Security | Github filtration to clean up security issues. |  | Dhruv | Complete |  | 2026-08-24
| Add .git ignore file | Github | .git ignore file added to our Github so that it ignores file types that it specifiies |  | Dhruv | Complete |  | 2026-08-24

## Weekly Summary
Weekly Summary Dashboard
Total Open Tasks | Tasks In Progress | Tasks Ready for Review
18 | 4 | 4
Tasks Merged | Tasks Completed | Completion Rate %
1 | 69 | 79.55%
Week | Team Member | Tasks Assigned | Tasks Completed | Tasks Merged | Tasks Carried Over | Major Accomplishments | Blockers | Support Needed Next Week
2026-06-01 | Joey | 1 | 1 | 0 | 1 | Dev Log & Tracker
2026-06-08 | Rafay | 4 | 4 | 0 | 0 | Double footer ¦ Update Buttons ¦ Artist Logos ¦ Nav Bar update
2026-06-22 | Rafay, Pratyank | 3 | 3 | 0 | 0 | Page spacing ¦ Clean up Mobile ¦ Mobile page spacing
2026-06-25 | Aakash | 1 | 1 | 0 | 0 | Shift Manual Auth to Firebase
2026-06-29 | Pratyank, Rafay, Aakash | 11 | 11 | 0 | 0 | Update Image ¦ Remove some sections ¦ Discord link ¦ Guidelines PDF ¦ Update Section ¦ Combine sections ¦ Featured Campaigns style ¦ Featured Campaigns Section ¦ Add Coolify to VPS ¦ Update platform T&S date ¦ Transfer/create submission terms of service and link to each Opportunity/contest page
2026-06-30 | Aakash | 1 | 1 | 0 | 0 | Switch domain to hostinger
2026-07-13 | Dhruv -> Jyotishmoy, Dhruv, Jyotishmoy, Pratyank, Jyotishmoy, Jyotishmoy, Aakash | 7 | 7 | 0 | 0 | Create New Accounts (Brand Owners) ¦ Create New Accounts (Fan Artists) ¦ Signup Workflow ¦ Authentication for librarians page ¦ Fix signup ¦ Fix Lib contest entry ¦ Get Submission flow ready
2026-07-16 | Rafay | 1 | 1 | 0 | 0 | Fix refresh glitch
2026-07-20 | Rafay, Pratyank, Praytank | 5 | 5 | 0 | 0 | Remove sections in Profile ¦ User name visibility fix ¦ Remove for Creators page on mobile ¦ Remove hardcoded parts of the Dashboard ¦ Add description and note to contest entry
2026-07-30 | Rafay -> Pratyank, Pratyank | 4 | 4 | 0 | 0 | Add how did you hear about us ¦ Replace hero image at Signup ¦ Fix submission tags ¦ Complete migration away from AWS
2026-08-02 | Pratyank | 1 | 1 | 0 | 0 | Link T&S to Lib contest
2026-08-10 | Pratyank, Praytank, Rafay | 6 | 6 | 0 | 0 | Remove Welcome Art ¦ Fix submission images in dashboard ¦ Individual submission pages ¦ Dashboard - View All Submissions ¦ Submission Detail View - Full Image + Form Metadata ¦ Fix dashboard images
2026-08-24 | Rafay, Pratyank | 4 | 4 | 0 | 0 | Prepare judging system ¦ Judging backend endpoints ¦ Judging next phase ¦ Copy judging password
2026-08-27 | Dhruv | 1 | 0 | 0 | 0 | Licensing workflow doc
2026-08-31 | Rafay | 1 | 1 | 0 | 0 | PDF image preview